## UAT_Test_Cases
TestCaseID | Module | TestScenario | TestDescription | Prerequisites | TestSteps | ExpectedResult | Priority | TestType | TestData | ExecutionStatus | ActualResult | PassFail | DefectID | ExecutedBy | ExecutionDate | Comments
UAT-001 | Vendor Onboarding | New Vendor Registration | Verify new vendor can register through self-service portal | Valid vendor information and documents available | 1. Access vendor registration portal 2. Complete mandatory fields 3. Upload required documents 4. Submit application 5. Verify confirmation email | Vendor application submitted successfully, approval workflow initiated, confirmation email received | High | Functional | Vendor_001, TAX123456789, Insurance_Cert_001.pdf | Not Executed
UAT-002 | Vendor Onboarding | Vendor Approval Workflow | Verify vendor approval workflow functions correctly | Vendor application submitted and pending approval | 1. Login as Finance approver 2. Review vendor application 3. Approve vendor with comments 4. Verify status change 5. Check notification sent to vendor | Vendor status changes to Active, notification sent, vendor can access portal | High | Workflow | Finance_User_001, Vendor_001 | Not Executed
UAT-003 | Purchase Orders | PO Creation with Auto-Approval | Create PO under $5000 and verify auto-approval | Active vendor exists, user has PO creation rights | 1. Login as procurement user 2. Create new PO for $3000 3. Add line items 4. Submit PO 5. Verify auto-approval and vendor notification | PO auto-approved, status changed to Sent_To_Vendor, notification sent | High | Business Rule | PO amount: $3000, Vendor_001, Item_001 | Not Executed
UAT-004 | Purchase Orders | PO Creation with Manual Approval | Create PO over $5000 and verify approval routing | Active vendor exists, finance approver available | 1. Create PO for $7500 2. Submit for approval 3. Verify routing to finance 4. Login as finance user 5. Approve PO 6. Verify vendor notification | PO routes to finance, requires approval, approved PO sent to vendor | High | Approval Workflow | PO amount: $7500, Finance_User_001 | Not Executed
UAT-005 | GRN Management | Digital GRN Recording | Record GRN using mobile interface with photo documentation | Approved PO sent to vendor, goods received | 1. Access GRN recording on mobile 2. Scan PO barcode 3. Enter received quantities 4. Take photos of goods 5. Submit GRN 6. Verify GRN completion | GRN recorded successfully, photos attached, PO status updated | High | Mobile Functionality | PO_001, Received_Qty: 95, Photos: 3 | Not Executed
UAT-006 | 3-Way Matching | Exact Match Auto-Approval | Verify invoice with exact PO/GRN match auto-approves | PO created, GRN recorded, matching invoice received | 1. Submit invoice matching PO and GRN exactly 2. Wait for auto-matching process 3. Verify invoice status 4. Check payment queue 5. Verify no manual intervention needed | Invoice auto-matched, status changed to Approved, added to payment queue | Critical | Automation | Invoice_001: $3000, matching PO_001 and GRN_001 | Not Executed
UAT-007 | 3-Way Matching | Tolerance Match with Notification | Verify invoice with 3% variance gets tolerance approval | PO for $1000, GRN for $970, invoice received | 1. Submit invoice for $970 2. System calculates 3% variance 3. Verify tolerance match approval 4. Check notification sent 5. Verify payment scheduling | Invoice approved with tolerance match, notification sent, payment scheduled | High | Business Logic | PO: $1000, GRN: $970, Invoice: $970 (3% variance) | Not Executed
UAT-008 | 3-Way Matching | Exception Handling for Large Variance | Verify invoice with >5% variance routes to exception queue | PO for $1000, GRN for $850, invoice received | 1. Submit invoice for $850 2. System detects 15% variance 3. Verify exception routing 4. Check exception queue 5. Verify manual review required | Invoice routed to exception queue, manual review required, variance details captured | High | Exception Handling | PO: $1000, GRN: $850, Invoice: $850 (15% variance) | Not Executed
UAT-009 | Payment Processing | Payment Run Simulation | Create and simulate payment run with multiple invoices | 5 approved invoices ready for payment | 1. Access payment run interface 2. Select date range 3. Apply vendor filters 4. Run simulation 5. Review results 6. Verify cash flow impact displayed | Simulation shows payment summary, cash flow impact, discount opportunities | High | Simulation | 5 invoices totaling $15,000, 2 with early pay discounts | Not Executed
UAT-010 | Payment Processing | Bank File Generation and SFTP | Generate and transmit bank file via SFTP | Approved payment run ready for generation | 1. Approve payment run 2. Generate bank file 3. Verify file format (ISO 20022) 4. Initiate SFTP transmission 5. Verify transmission confirmation 6. Check bank acknowledgment | Bank file generated correctly, transmitted via SFTP, confirmation received | Critical | Integration | Payment run with $25,000 total, 15 payments | Not Executed
UAT-011 | Supplier Portal | Vendor Order Status Visibility | Verify vendor can view real-time order status | Active vendor account, existing orders in system | 1. Login to supplier portal 2. Navigate to order dashboard 3. Verify PO status display 4. Check GRN status 5. Verify payment status 6. Test search and filter functions | All order statuses displayed correctly, real-time updates, functional search | Medium | Portal Functionality | Vendor_001 with 3 orders in different statuses | Not Executed
UAT-012 | Supplier Portal | Invoice Submission via Portal | Submit invoice through supplier portal | Vendor logged in, valid PO exists | 1. Navigate to invoice submission 2. Select PO from dropdown 3. Upload invoice PDF 4. Complete invoice details form 5. Submit invoice 6. Verify confirmation and tracking | Invoice submitted successfully, confirmation displayed, tracking number provided | Medium | Portal Functionality | PO_001, Invoice_PDF_001.pdf | Not Executed
UAT-013 | Security | Role-Based Access Control | Verify RBAC prevents unauthorized access | Users with different roles configured | 1. Login as Procurement user 2. Attempt to access Finance functions 3. Verify access denied 4. Login as Finance user 5. Verify appropriate access granted 6. Test menu restrictions | Access properly restricted by role, appropriate error messages displayed | Critical | Security | Procurement_User_001, Finance_User_001 | Not Executed
UAT-014 | Audit Trail | Transaction Audit Logging | Verify all transactions are properly audited | System configured for audit logging | 1. Perform vendor creation 2. Create and approve PO 3. Record GRN 4. Process payment 5. Check audit log entries 6. Verify completeness of audit trail | All transactions logged with user, timestamp, old/new values | High | Compliance | Complete transaction flow from vendor to payment | Not Executed
UAT-015 | Integration | ERP Data Synchronization | Verify master data sync between VPPS and ERP | ERP integration configured and active | 1. Update vendor data in ERP 2. Trigger synchronization 3. Verify data updated in VPPS 4. Check sync log for errors 5. Verify bidirectional sync 6. Test error handling for sync failures | Data synchronized correctly, errors logged, manual intervention triggered when needed | High | Integration | Vendor_001 master data changes | Not Executed
UAT-016 | Performance | Payment Run Processing Speed | Verify payment run processes within SLA timeframes | 500 approved invoices ready for payment | 1. Create payment run with 500 invoices 2. Start processing timer 3. Execute payment run 4. Record completion time 5. Verify all payments processed 6. Check system performance during processing | Payment run completes within 10 minutes, system responsive during processing | Medium | Performance | 500 invoices, various vendors and amounts | Not Executed
UAT-017 | Exception Management | Exception Resolution Workflow | Process and resolve matching exceptions | Exception exists in queue from previous test | 1. Access exception management queue 2. Select exception for review 3. Analyze variance details 4. Add resolution notes 5. Override or reject decision 6. Verify workflow completion | Exception resolved, decision recorded, invoice status updated appropriately | High | Workflow | Exception with 15% quantity variance | Not Executed
UAT-018 | Notifications | Email Notification System | Verify email notifications sent for key events | Email system configured, valid email addresses | 1. Submit PO for approval 2. Check approval notification email 3. Approve PO 4. Verify vendor notification 5. Test exception notifications 6. Verify payment confirmations | All notifications sent correctly with proper content and recipients | Medium | Communication | Valid email addresses for all user types | Not Executed
UAT-019 | Reporting | KPI Dashboard Functionality | Verify KPI dashboard displays accurate real-time data | Transaction data available, dashboard configured | 1. Access KPI dashboard 2. Verify payment cycle metrics 3. Check error rate statistics 4. Validate processing volumes 5. Test date range filters 6. Verify data refresh functionality | Dashboard displays accurate KPIs, filters work correctly, data refreshes properly | Medium | Reporting | Historical transaction data for KPI calculations | Not Executed
UAT-020 | Data Export | Transaction Data Export | Export transaction data for external analysis | Transaction data available, export permissions granted | 1. Access export functionality 2. Select date range and filters 3. Choose export format (Excel) 4. Generate export file 5. Download and verify file contents 6. Test data completeness | Export completes successfully, file contains correct data, format is valid | Low | Data Management | 30 days of transaction data | Not Executed